## 00_README
Forensa Traceability Master — v2.0
Pack version: v2.0 ELABORATED · 2026-05-18 05:15 BST
Codebase: forensa/ · Doc pack: forensa/docs/
Authoritative against HEAD CP9.51 (d7d9aaa)
MOST IMPORTANT RULES
Rule A.10 — open BRD + USE_CASES + TRACEABILITY_MATRIX before each CP. Pick CP by which named ID needs closing next.
Rule A.11 — every CP commit must close ≥ 1 named ID (BR-N / US-FN / UC-N / RT-FN / SCR-FN). Commit message names IDs. LIVE doc records CP against IDs. CPs that close no named ID are labelled CPx.y-tooling and do NOT advance the scoreboard.
Sheet index
Sheet | Content
00_README | This page
01_Identifier_Map | Prefix scheme — BG / BR / UC / US-F / SCR-F / API-F / DB-F / TEST-F / EVID-F / RT-F / IMP-F / EVAL-F / R-F / OPT-F / NFR / CP
02_BG_to_BR | Business goals + BG → BR weighted contribution matrix
03_BR_status | BR-01..BR-14 status board
04_UC_status | UC-01..UC-10 status board
05_US_status | US-F01..F32 user-story roll-up
06_SCR_index | SCR-F01..F10 console screen index
07_API_DB_Evidence | API → DB → Evidence map
08_RT_index | RT-F01..F22 — 12-column trace index
09_TEST_coverage | TEST-F01..F40+ coverage map
10_EVID_index | EVID-F01..F06 evidence artefacts
11_IMP_forward_queue | IMP-F* enhancements per RT
12_Risk_register | R-F01..F12 risk register
13_Change_log | Cross-doc change log

## 01_Identifier_Map
Identifier Map — canonical · see 02_brd/BRD_IDENTIFIER_MAP.md
Prefix | Meaning | Range | Source / status | Notes
BG | Business Goal | BG-F01..F06 | NEW v2.0 | Drives BG→BR matrix
BR | Business Requirement | BR-01..BR-14 | BR-01..F13 pre-existing; BR-14 NEW v2.0 | BR-14 = Operator Console Web + PWA, native deferred Phase 14+
UC | Use Case | UC-01..UC-10 | UC-01..F08 pre-existing; UC-09, UC-10 NEW v2.0 | UC-09 console journey; UC-10 multi-tenant auth
US-F | User Story | US-F01..F32 | NEW (numbered) in 005-01-H18 v1; extended in v2.0 | 7 epics A..G
SCR-F | Console Screen | SCR-F01..F10 | NEW v2.0 | List-views-as-top-nav
API-F | Backend API endpoint | API-F01..F15 | Existing + planned F11..F15 | Auth, tabletop, M&A, metrics
DB-F | Database entity | DB-F01..F08 | Derived from alembic migrations | DB-F08 sessions planned Phase 10
TEST-F | Test family | TEST-F01..F40+ | Pre-existing 38 + planned UI-driving | TEST-F30..F40 planned CP9.52..Phase 10
EVID-F | Evidence artefact | EVID-F01..F06 | NEW v2.0 | Receipt, EvidencePack, AnchorEvidence, MaDiligenceExport, TabletopResult, Narrative
RC-F | Review Comment | RC-F01..F30 | Derived from docs/reviews/ | Used in RT cross-refs
IMP-F | Forward-queue enhancement | IMP-F01..F36+ | Pre-existing convention | Maps 1:1 to NEW-P phase items
EVAL-F | AI evaluation gate | EVAL-F01, F02 | NEW v2.0 | Narrative quality + injection defence
RT-F | Trace Row bundle | RT-F01..F22 | F01..F18 pre-existing; F19..F22 NEW v2.0 | 12-column expansion
OPT-F | Competitor option | OPT-F01..F08 | From COMPETITIVE_LANDSCAPE | OPT-F01 = Forensa
R-F | Risk register entry | R-F01..F12 | NEW v2.0 | L × I scored; R-F12 = doc drift
NFR | Non-Functional Requirement | NFR-01..F10 | Pre-existing; NFR-09, F10 formalised v2.0 | Accessibility + multi-tenant isolation
CP | Checkpoint commit | CP1.0..CP14.x+ | Pre-existing project convention | Rule A.11: ≥1 named ID per CP

## 02_BG_to_BR
Business Goals + BG → BR weighted contribution
Business Goals
ID | Goal | Quantification | Owner | Linked BRs
BG-F01 | Reduce regulator-inquiry response time | -90% vs baseline | P-COMP | BR-01, F04, F05, F10, F11
BG-F02 | Cryptographic chain integrity verifiable offline | 100% pack verifiability | P-PLAT | BR-01, F02, F06
BG-F03 | Close EU AI Act Art 12 / DORA Art 30 gaps | Art 12 logging + Art 18 retention compliant | P-COUNSEL | BR-01, F04, F05, F12
BG-F04 | Enable non-technical operator workflows | 6 personas complete task without engineer | Product Owner | BR-14
BG-F05 | Support M&A diligence + legal hold export | Diligence turnaround ≤ 4 hours | P-ACQ + P-COUNSEL | BR-05, F13
BG-F06 | Demonstrate AI safety surface | EVAL-F02 ≥ 0 leaks on N=500 | AI Lead | BR-10, F11
BG → BR weighted contribution matrix (cols sum to 100% per BG)
BR | BG-F01 | BG-F02 | BG-F03 | BG-F04 | BG-F05 | BG-F06
BR-01 Tamper-evident recording | 25% | 30% | 25% | 5% | 10% | 5%
BR-02 Multi-party identity binding | 5% | 25% | 10% | 5% | 5% | 5%
BR-03 Reasoning capture (AER) | 10% | 5% | 10% | 5% | 5% | 15%
BR-04 Policy snapshot binding | 15% | 5% | 20% | 5% | 5% | 5%
BR-05 Regulator-grade export | 25% | 10% | 25% | 10% | 25% | 5%
BR-06 Merkle ledger + RFC 3161 TSA | 5% | 20% | 5% | 5% | 5% | 5%
BR-07 Multi-agent provenance (deferred) | — | — | — | — | — | 5%
BR-08 Omniverse replay (deferred) | — | — | — | — | — | —
BR-09 AWS bulk backfill | 5% | — | 5% | — | 5% | —
BR-10 Investigator narrative | 5% | — | — | 5% | 10% | 25%
BR-11 Counterfactual narrative | 5% | — | — | — | 10% | 25%
BR-12 Tabletop simulation | — | — | 5% | 5% | — | 5%
BR-13 M&A diligence export | — | — | — | 5% | 25% | —
BR-14 Operator Console (Web + PWA, native deferred) | — | 5% | — | 50% | — | —

## 03_BR_status
BR-01..BR-14 status board (HEAD CP9.51)
BR | Title | Status | Closing CP / commit | Test families | Notes
BR-01 | Tamper-evident event recording | IMPLEMENTED+TESTED | Phase 1 + CP9.16/9.17/9.18 | TEST-F01..F04 + F19 | DB-level append-only triggers
BR-02 | Multi-party identity binding | IMPLEMENTED+TESTED | CP9.18a/b/c (ec81920) | TEST-F07 21 sign | v1.2 said PARTIAL — corrected v2.0 §0.3
BR-03 | Reasoning capture (AER) | IMPLEMENTED+TESTED | Phase 1 | TEST-F06 50 | Named finding RC-F14 / IMP-F14
BR-04 | Policy snapshot at decision time | IMPLEMENTED+TESTED | Phase 3 + CP9.15 | TEST-F08 22 + F09 6 | Append-only triggers
BR-05 | Regulator-grade export | IMPLEMENTED+TESTED | CP9.21a + CP9.21b | TEST-F12 72 | JSON-LD + A4 PDF
BR-06 | Merkle ledger + RFC 3161 TSA | IMPLEMENTED+TESTED | CP9.19 + CP9.51 (d7d9aaa) | TEST-F10 22 + F11 25 | v1.2 said DEFERRED — corrected v2.0 §0.3
BR-07 | Multi-agent provenance (LangGraph) | DEFERRED Phase 12 | — | — | By design
BR-08 | Omniverse physical replay | DEFERRED Phase 13 | — | — | Always stretch
BR-09 | AWS bulk backfill | PARTIAL — in-process proven; AWS Phase 12 | CP8.2 (6452/sec) | TEST-F05 | Kafka + S3 Phase 12
BR-10 | Investigator narrative | IMPLEMENTED+TESTED for API; NL UX DEFERRED Phase 13 | CP9.1 + CP9.20 | TEST-F13 19 | Live Gemini 2.5 Pro + 4-layer defence
BR-11 | Counterfactual narrative | IMPLEMENTED+TESTED | CP9.1 | TEST-F13 rolled | Semantic guardrail IMP-F11 Phase 12
BR-12 | Tabletop simulation | IMPLEMENTED+TESTED | CP9.29 | TEST-F15 19 | DORA Article 30 surface
BR-13 | M&A diligence export | IMPLEMENTED+TESTED | CP9.28 | TEST-F16 17 | ma_root_hash composability
BR-14 | Operator Console (Web + PWA, native deferred Phase 14+) | PARTIAL — 3 screens MVP; CP9.52 closes v1.x | CP9.52 planned | TEST-F30..F38 planned | NEW v2.0

## 04_UC_status
UC-01..UC-10 status board
UC | Subject | Stories | Status | Primary persona
UC-01 | Regulator evidence pack (canonical demo) | US-F07, F17, F18, F19, F20 | IMPLEMENTED+TESTED (Compliance UI PLANNED CP9.52) | P-COMP
UC-02 | Customer dispute reconstruction | US-F03, F08, F17 | IMPLEMENTED+TESTED | P-COUNSEL
UC-03 | Multi-agent chain audit | US-F24 (deferred) | PARTIAL (single-agent; LangGraph Phase 12) | P-SEC
UC-04 | Policy drift detection | US-F11, F12 | IMPLEMENTED+TESTED | P-COMP
UC-05 | Model deprecation evidence preservation | US-F01, F17 | IMPLEMENTED+TESTED in-process; AWS DEFERRED | P-COMP, P-PLAT
UC-06 | Tabletop incident response (DORA Article 30) | US-F21, F22, F23 | IMPLEMENTED+TESTED backend; UI PLANNED CP9.55 | P-SEC
UC-07 | M&A due diligence | US-F25, F26 | IMPLEMENTED+TESTED backend; UI PLANNED CP9.56 | P-ACQ
UC-08 | Prompt injection investigation | (rolled into narrative defence tests) | IMPLEMENTED+TESTED | P-SEC
UC-09 | Operator console journey (NEW v2.0) | US-F28, F29, F30, F19 | PLANNED CP9.52 | P-COMP
UC-10 | Multi-tenant authenticated access (NEW v2.0) | US-F32 | DEFERRED Phase 10 CP10.1..CP10.4 | P-PLAT

## 05_US_status
US-F01..US-F32 user-story roll-up
US | Title | Persona | BR | SCR | API | Status | Closing CP
US-F01 | Agent action ingested as signed Receipt | P-PLAT | BR-01, F02 | — | API-F01 | IMPLEMENTED+TESTED | Phase 1 + CP9.18
US-F02 | Retry-safe ingest | P-PLAT | BR-01 / NFR-08 | — | API-F01 | IMPLEMENTED+TESTED | CP9.17
US-F03 | Tenant signature verification | P-AUD | BR-02 | SCR-F03 | — | IMPLEMENTED+TESTED | Phase 2
US-F04 | Agent identity signature | P-AUD | BR-02 | — | API-F01 | IMPLEMENTED+TESTED | CP9.18a/b/c
US-F05 | Reasoning capture in event | P-AUD | BR-03 | — | API-F01 | IMPLEMENTED+TESTED | Phase 1
US-F06 | OTel GenAI envelope ingest | P-PLAT | BR-01, F03 | — | API-F01 | IMPLEMENTED+TESTED (named finding) | Phase 1
US-F07 | Receipt list view for tenant | P-COMP | BR-01 | SCR-F02 | API-F05 | PARTIAL (full timeline CP9.52) | Phase 4 (basic)
US-F08 | Single-receipt detail with verification | P-AUD | BR-01, F06 | SCR-F03 | API-F06 | PARTIAL (tabs CP9.52) | Phase 4 (basic)
US-F09 | Policy bundle snapshot at decision | P-AUD | BR-04 | — | API-F01 | IMPLEMENTED+TESTED | Phase 3
US-F10 | Policy bundle approval workflow | P-COMP | BR-04 | — | — | IMPLEMENTED+TESTED | CP9.15
US-F11 | Policy drift surfaced in narrative | P-COMP | BR-04, F10 | SCR-F08 | API-F13 | IMPLEMENTED+TESTED | CP9.1
US-F12 | Policy replay never returns live state | P-AUD | BR-04 | — | — | IMPLEMENTED+TESTED | Phase 3
US-F13 | Hash chain verifiable offline | P-REG | BR-06 | — | — | IMPLEMENTED+TESTED | Phase 2
US-F14 | Daily RFC 3161 anchor against FreeTSA | P-PLAT | BR-06 | SCR-F05 | API-F08 | IMPLEMENTED+TESTED | CP9.19
US-F15 | Cert-chain verification of TSR | P-REG | BR-06 | — | — | IMPLEMENTED+TESTED | CP9.51 (d7d9aaa)
US-F16 | Raw TSR DER bytes downloadable | P-AUD | BR-06 | SCR-F05 | API-F08 | IMPLEMENTED+TESTED | CP9.27
US-F17 | JSON-LD evidence pack | P-COMP | BR-05 | SCR-F04 | API-F07 | IMPLEMENTED+TESTED | Phase 6
US-F18 | Regulator-grade PDF | P-COMP | BR-05 | SCR-F04 | API-F07 | IMPLEMENTED+TESTED | CP9.21a/b
US-F19 | Evidence pack Compliance view | P-COMP | BR-05, F14 | SCR-F04 | API-F07 | PLANNED | CP9.52d
US-F20 | Offline pack verification | P-REG | BR-05, F06 | — | — | IMPLEMENTED+TESTED | Phase 6
US-F21 | Tabletop drill via API | P-SEC | BR-12 | — | API-F11 | IMPLEMENTED+TESTED | CP9.29
US-F22 | Tabletop replay window | P-SEC | BR-12 | — | API-F12 | IMPLEMENTED+TESTED | CP9.29
US-F23 | Tabletop UI in Console | P-SEC | BR-12, F14 | SCR-F06 | API-F11 | PLANNED CP9.55 | —
US-F24 | LangGraph multi-agent capture | P-SEC | BR-07 | — | — | DEFERRED Phase 12 | —
US-F25 | M&A diligence export bundle | P-ACQ | BR-13 | — | API-F09 | IMPLEMENTED+TESTED | CP9.28
US-F26 | M&A diligence UI in Console | P-ACQ | BR-13, F14 | SCR-F07 | API-F09, F10 | PLANNED CP9.56 | —
US-F27 | Free-text NL query in Console | P-COMP | BR-10 | — | API-F13 | DEFERRED Phase 13 | —
US-F28 | Persona-aware landing | all | BR-14 | SCR-F01 | — | PLANNED CP9.52e | —
US-F29 | Enterprise timeline (list-views-as-top-nav) | P-COMP | BR-14 | SCR-F02 | API-F05 | PLANNED CP9.52a/b | —
US-F30 | Receipt detail tabbed view | P-AUD | BR-14 | SCR-F03 | API-F06 | PLANNED CP9.52c | —
US-F31 | PWA installable to home screen | P-COMP | BR-14 | all | — | PLANNED CP9.52f | —
US-F32 | Multi-tenant auth + tenant picker | P-PLAT | BR-02, F14 | SCR-F09 | API-F14 | DEFERRED Phase 10 CP10.1..CP10.4 | —

## 06_SCR_index
SCR-F01..SCR-F10 Console screen index (BR-14)
SCR | Title | Route | Persona | Status | API | Notes
SCR-F01 | Persona landing + tenant picker | / | all | PLANNED CP9.52 | API-F05 (preview) | Persona-aware cards
SCR-F02 | Receipts timeline | /receipts | P-COMP, P-AUD, P-SEC | PARTIAL (table exists; timeline CP9.52) | API-F05 | List-views-as-top-nav
SCR-F03 | Receipt detail with tabs | /receipts/[id] | P-AUD, P-SEC | PARTIAL (page exists; tabs CP9.52) | API-F06 | Summary / Proof / Raw
SCR-F04 | Evidence pack generator + Compliance view | /evidence | P-COMP, P-COUNSEL | PARTIAL (toggle CP9.52) | API-F07 | Compliance default
SCR-F05 | Anchors view | /anchors | P-AUD, P-PLAT | PLANNED CP9.53 | API-F08 | Per-day TSR DER download
SCR-F06 | Tabletop drill / replay UI | /tabletop | P-SEC | PLANNED CP9.55 | API-F11, F12 | —
SCR-F07 | M&A diligence workspace | /diligence | P-ACQ, P-COUNSEL | PLANNED CP9.56 | API-F09, F10 | Create / list / detail / download
SCR-F08 | Narrative viewer | /narratives | P-COMP, P-SEC | PLANNED CP9.57 | API-F13 | Window picker + Explain CTA
SCR-F09 | Login / auth surface | /login | all | PLANNED Phase 10 CP10.1 | API-F14 | SSO + bearer fallback
SCR-F10 | Status / ops dashboard | /status | P-PLAT | PLANNED CP9.58 | API-F15 | Ingest + sig latency + anchor health

## 07_API_DB_Evidence
API → DB → Evidence map
API | Method / Path | Request schema | Response | DB writes | Evidence emitted | Timeout / SLO
API-F01 | POST /v1/events | Event | EventCreatedResponse | DB-F01 events, F02 receipts, F03 ref, F06 idempotency | EVID-F01 Receipt | 5s soft, 15s hard
API-F05 | GET /v1/receipts | query (tenant_id, limit, before, after) | ReceiptListResponse cursor | (read DB-F02) | (rolls EVID-F01) | 2s
API-F06 | GET /v1/receipts/{id} | path id | ReceiptDetail | (read DB-F02) | (rolls EVID-F01) | 2s
API-F07 | GET /v1/evidence-packs | query · Accept: jsonld¦pdf | EvidencePack JSON-LD OR application/pdf | (read DB-F02, F04) | EVID-F02 EvidencePack | 30s; 8s p95
API-F08 | GET /v1/anchors[/{id}] | query · Accept: json¦timestamp-reply | AnchorList / AnchorEvidence | (read DB-F04) | EVID-F03 AnchorEvidence | 5s
API-F09 | POST /v1/exports/ma-diligence | MaDiligenceRequest | MaDiligenceExport | DB-F05 (optional async) | EVID-F04 MaDiligenceExport | 60s; async planned
API-F10 | POST/GET /v1/exports/ma-diligence/jobs | per spec | per spec | DB-F05 | EVID-F04 | 5s
API-F11 | POST /v1/tabletop/simulate | TabletopScenario | TabletopResult | (no persist) | EVID-F05 TabletopResult | 30s
API-F12 | POST /v1/tabletop/replay-window | ReplayRequest | ReplayResult | (no persist) | EVID-F05 | 30s
API-F13 | POST /v1/narratives | NarrativeRequest | NarrativeResponse | (no persist) | EVID-F06 Narrative | 60s (LLM)
API-F14 | POST /v1/auth/login (planned Phase 10) | LoginRequest | LoginResponse + cookie | DB-F08 sessions (planned) | — | 5s
API-F15 | GET /v1/metrics (planned) | — | metrics | (read) | — | 2s

## 08_RT_index
RT-F01..RT-F22 — 12-column traceability index
RT | Subject | BG | BR | UC | SCR | API | DB | TEST | EVID | IMP | EVAL | Status | Notes
RT-F01 | Event ingest pipeline | BG-F01, F02 | BR-01 | UC-01..08 | (backend) | API-F01 | DB-F01/F02 | TEST-F01..F04 | EVID-F01 | IMP-F01/F02 | — | IMPLEMENTED+TESTED
RT-F02 | In-process throughput | BG-F02 | BR-01, F09 | UC-05 | — | API-F01 | DB-F01 | TEST-F05 | (rolls F01) | IMP-F09 | — | IMPLEMENTED+TESTED (in-process); AWS DEFERRED Phase 12 | 6452 events/sec
RT-F03 | Reasoning capture | BG-F03 | BR-03 | UC-01, 08 | SCR-F03 | API-F01 | DB-F02 | TEST-F06 | (rolls F01) | IMP-F14 | — | IMPLEMENTED+TESTED with named finding | Normaliser conflation
RT-F04 | Multi-party identity | BG-F02 | BR-02 | UC-02 | SCR-F03 | API-F01 | — | TEST-F07 | EVID-F01 | IMP-F15 | — | IMPLEMENTED+TESTED | CP9.18a/b/c
RT-F05 | Policy snapshot binding | BG-F03 | BR-04 | UC-01, 04, 08 | SCR-F03 | API-F01 | DB-F03 | TEST-F08 | (rolls F01) | IMP-F16 | — | IMPLEMENTED+TESTED
RT-F06 | Bundle approval workflow | BG-F03 | BR-04 | UC-04 | (admin) | (admin) | DB-F03 | TEST-F09 | (cross) | IMP-F17 | — | IMPLEMENTED+TESTED | CP9.15
RT-F07 | Hash chain primitive | BG-F02 | BR-06 | UC-01 | SCR-F03 | (internal) | DB-F02 | TEST-F10 | EVID-F01 | IMP-F03 | — | IMPLEMENTED+TESTED
RT-F08 | RFC 3161 TSA anchoring | BG-F02 | BR-06 | UC-01 | SCR-F05 | API-F08 | DB-F04 | TEST-F11 (25) | EVID-F03 | IMP-F12 | — | IMPLEMENTED+TESTED (CP9.51 cert chain)
RT-F09 | Regulator-grade export | BG-F01 | BR-05 | UC-01, 02, 07 | SCR-F04 | API-F07 | DB-F02, F04 (read) | TEST-F12 (72) | EVID-F02 | IMP-F04 | — | IMPLEMENTED+TESTED
RT-F10 | Live narrative + injection defence | BG-F06 | BR-10, F11 | UC-01, 04, 08 | SCR-F08 (planned) | API-F13 | (no persist) | TEST-F13 (19) | EVID-F06 | IMP-F11 | EVAL-F01, F02 | IMPLEMENTED+TESTED
RT-F11 | Receipt list pagination | BG-F04 | BR-01 | UC-01 | SCR-F02 | API-F05 | DB-F02 (read) | TEST-F14 | (rolls F01) | IMP-F18 | — | IMPLEMENTED+TESTED (cursor); OpenSearch DEFERRED
RT-F12 | Tabletop simulation | BG-F03 | BR-12 | UC-06 | SCR-F06 (planned) | API-F11, F12 | (no persist) | TEST-F15 (19) | EVID-F05 | IMP-F19 | — | IMPLEMENTED+TESTED | CP9.29
RT-F13 | M&A diligence export | BG-F05 | BR-13 | UC-07 | SCR-F07 (planned) | API-F09, F10 | DB-F05 | TEST-F16 (17) | EVID-F04 | IMP-F05/F06/F20 | — | IMPLEMENTED+TESTED | CP9.28
RT-F14 | Retry-safe ingest | BG-F02 | BR-01 / NFR-08 | UC-01, 05 | (backend) | API-F01 | DB-F06 | TEST-F17 (54) | (cross) | IMP-F23/F24 | — | IMPLEMENTED+TESTED | CP9.17
RT-F15 | Multi-tenant isolation | BG-F02 | NFR-10 | all | all SCR-F | all API-F | RLS all tables | TEST-F18 | (cross) | IMP-F25 | — | IMPLEMENTED+TESTED | 404-not-403 to avoid leak
RT-F16 | PG triggers + partial UNIQUE | BG-F02 | BR-01 / NFR-01 | UC-01 | — | (internal) | DB-F03, F07 | TEST-F19 (14) | (rolls F01) | — | — | IMPLEMENTED+TESTED | CP9.16-PG-up
RT-F17 | LangGraph multi-agent provenance | BG-F06 | BR-07 | UC-03, 08 | (future) | (future) | (future) | (future) | (future) | IMP-F07 | — | DEFERRED Phase 12
RT-F18 | Omniverse physical replay | BG-F06 | BR-08 | (out) | (future) | (future) | — | — | — | IMP-F08 | — | DEFERRED Phase 13 | Stretch
RT-F19 | Operator Console enterprise list views (NEW v2.0) | BG-F04 | BR-14 | UC-09 | SCR-F01..F08 | API-F05, F06, F07, F08, F13 | (read) | TEST-F30..F35 planned | (presents EVID-F01..F06) | IMP-F26/F27/F28 | — | PLANNED CP9.52 | List-views-as-top-nav; no sessionStorage
RT-F20 | PWA installable shell (NEW v2.0) | BG-F04 | BR-14 | UC-09 | all SCR-F | (client SW) | (client cache) | TEST-F36..F38 planned | — | IMP-F29/F30 | — | PLANNED CP9.52 | Manifest + service worker
RT-F21 | Tabletop / M&A / Narrative Console UI (NEW v2.0) | BG-F04 | BR-12, F13, F10, F14 | UC-06, 07, 04 | SCR-F06, F07, F08 | API-F11, F12, F09, F10, F13 | DB-F05 | TEST-F39 planned | EVID-F04, F05, F06 | IMP-F31/F32/F33 | EVAL-F01 | PLANNED CP9.55..CP9.57
RT-F22 | Multi-tenant auth surface (NEW v2.0) | BG-F02, F04 | BR-02, F14 | UC-10 | SCR-F09 + tenant picker | API-F14 | DB-F08 (planned) | TEST-F40 planned | — | IMP-F34/F35/F36 | — | DEFERRED Phase 10 CP10.1..CP10.4 | SSO + bearer fallback

## 09_TEST_coverage
TEST-F01..TEST-F40+ coverage map
TEST family | Subject | Cases | Layer | Status
TEST-F01..F04 | Ingest happy / 422 / 401 / idempotency shape | varies | pytest unit + integration | IMPLEMENTED+TESTED
TEST-F05 | Load test 6452/sec | 2 functional | scripts/load_test.py | IMPLEMENTED+TESTED
TEST-F06 | Schema + OTel normaliser | 50 (32+18) | pytest unit | IMPLEMENTED+TESTED
TEST-F07 | Signature + agent-sig | 21 | pytest unit + integration | IMPLEMENTED+TESTED
TEST-F08 | Snapshot + replay | 22 (17+5) | pytest integration | IMPLEMENTED+TESTED
TEST-F09 | Bundle approval triggers | 6 | PG integration | IMPLEMENTED+TESTED
TEST-F10 | Merkle chain property-based | 22 | hypothesis | IMPLEMENTED+TESTED
TEST-F11 | RFC 3161 TSA + cert chain | 25 (11+14 CP9.51) | pytest unit + live integration | IMPLEMENTED+TESTED
TEST-F12 | Evidence pack JSON-LD + PDF | 72 | pytest unit + integration | IMPLEMENTED+TESTED
TEST-F13 | Narrative + injection defence | 19 (16+3 neg) | pytest unit + integration | IMPLEMENTED+TESTED
TEST-F14 | Receipt list cursor pagination | varies | pytest integration | IMPLEMENTED+TESTED
TEST-F15 | Tabletop | 19 (13+6) | pytest unit + integration | IMPLEMENTED+TESTED
TEST-F16 | M&A export | 17 (12+5) | pytest unit + integration | IMPLEMENTED+TESTED
TEST-F17 | Idempotency | 54 (35+19) | pytest unit + integration | IMPLEMENTED+TESTED
TEST-F18 | Cross-tenant 403/404 | per route | pytest integration | IMPLEMENTED+TESTED
TEST-F19 | PG triggers + partial UNIQUE | 14 | PG integration | IMPLEMENTED+TESTED
TEST-F20..F29 | (Reserved BR-07/08/09 AWS) | — | — | DEFERRED
TEST-F30 | SCR-F01 persona landing | 4 happy + 2 neg × 3 browsers | Playwright UI-driving | PLANNED CP9.52
TEST-F31 | SCR-F02 receipts timeline | 8 happy + 4 neg × 3 browsers | Playwright UI-driving | PLANNED CP9.52
TEST-F32 | SCR-F03 receipt-detail tabs | 6 happy + 2 neg × 3 browsers | Playwright UI-driving | PLANNED CP9.52
TEST-F33 | SCR-F04 Compliance view | 5 happy + 2 neg × 3 browsers | Playwright UI-driving | PLANNED CP9.52
TEST-F34 | List-views-as-top-nav (+ anti-pattern check) | 5 + 1 sessionStorage-absent assertion | Playwright | PLANNED CP9.52
TEST-F35 | Responsive mobile width | 3 happy + 2 neg | Playwright mobile | PLANNED CP9.52
TEST-F36 | PWA manifest validity | field validation | structural | PLANNED CP9.52
TEST-F37 | Service worker registration + scope | 3 cases | Playwright + manual | PLANNED CP9.52
TEST-F38 | PWA offline shell + 24h-stale banner | 5 cases | Playwright + manual | PLANNED CP9.52
TEST-F39 | Tabletop / M&A / Narrative UI | ~24 cases × 3 browsers | Playwright | PLANNED CP9.55..CP9.57
TEST-F40 | Auth + login + tenant picker | ~10 cases × 3 browsers + pytest | Playwright + pytest | PLANNED Phase 10

## 10_EVID_index
EVID-F01..EVID-F06 evidence artefact index
EVID | Artefact | Bound by | Produced by API | Verifiable offline?
EVID-F01 | Receipt | receipt_hash + signature_b64 | API-F01 | Yes — verify_chain()
EVID-F02 | EvidencePack | root_hash | API-F07 | Yes — verify_evidence_pack()
EVID-F03 | AnchorEvidence | TSR DER bytes + cert chain | API-F08 | Yes — openssl ts -verify OR verify_rfc3161_timestamp_response()
EVID-F04 | MaDiligenceExport | ma_root_hash | API-F09 | Yes — verify_ma_diligence_export()
EVID-F05 | TabletopResult | (not persisted; one-shot) | API-F11, F12 | Returned to caller; no chain mutation
EVID-F06 | Narrative | (not persisted; LLM output) | API-F13 | Replayable given prompt + model version

## 11_IMP_forward_queue
IMP-F* forward queue — enhancements per RT
IMP | Description | RT cross-ref | Phase
IMP-F01 | Payload-size limit (additional to schema) | RT-F01 | 12
IMP-F02 | OTel traceparent propagation in ingest | RT-F01 | 12
IMP-F03 | Merkle tree (RFC 6962) for inclusion proofs | RT-F07 | 12
IMP-F04 | Detached platform signature on pack | RT-F09 | 11
IMP-F05 | M&A export detached platform signature | RT-F13 | 11
IMP-F06 | M&A export at-rest encryption | RT-F13 | 11
IMP-F07 | LangGraph adapter | RT-F17 | 12
IMP-F08 | Omniverse / Isaac Sim adapter | RT-F18 | 13
IMP-F09 | Kafka + S3 + EventBridge BR-09 full topology | RT-F02 | 12
IMP-F11 | Semantic hallucination guardrail on narrative | RT-F10 | 12
IMP-F12 | Second TSA fallback (in addition to FreeTSA) | RT-F08 | 11
IMP-F14 | Separate forensa.reasoning from gen_ai.response.text | RT-F03 | 11
IMP-F15 | KMS-rooted DEK for tenant signing keys | RT-F04 | 11
IMP-F16 | OPA integration for richer policy expressions | RT-F05 | 12
IMP-F17 | Admin UI for bundle approval workflow | RT-F06 | 11
IMP-F18 | OpenSearch backend for scalable search | RT-F11 | 12
IMP-F19 | Tabletop diff report (sim vs actual) | RT-F12 | 12
IMP-F20 | M&A export async-job mode (current sync only) | RT-F13 | 12
IMP-F23 | Idempotency cleanup cron | RT-F14 | 11
IMP-F24 | Production-wiring PostgresIdempotencyStore | RT-F14 | 11
IMP-F25 | Row-level security DB enforcement | RT-F15 | 11
IMP-F26 | Timeline status chips with consistent color tokens | RT-F19 | 9.52
IMP-F27 | Receipt-detail Summary/Proof/Raw tabs | RT-F19 | 9.52
IMP-F28 | Compliance-view toggle on /evidence | RT-F19 | 9.52
IMP-F29 | PWA install prompt UX | RT-F20 | 9.52
IMP-F30 | 24h-stale-warning banner offline | RT-F20 | 9.52
IMP-F31 | Tabletop drill UI | RT-F21 | 9.55
IMP-F32 | M&A diligence workspace UI | RT-F21 | 9.56
IMP-F33 | Narrative viewer UI | RT-F21 | 9.57
IMP-F34 | SCIM provisioning | RT-F22 | 11
IMP-F35 | SAML SSO | RT-F22 | 11
IMP-F36 | Tenant picker UX | RT-F22 | 10

## 12_Risk_register
R-F01..R-F12 Risk register
ID | Risk | L (1-5) | I (1-5) | Score | Mitigation | Owner / Phase
R-F01 | FreeTSA outage causes daily anchor failure | 3 | 4 | 12 | Deferred-tombstone fallback (CP9.19); 2nd TSA fallback IMP-F12 Phase 11 | P-PLAT / 9
R-F02 | Prompt-injection bypass on narrative endpoint | 2 | 5 | 10 | 4-layer defence (CP9.1); EVAL-F02 corpus to N=500 (Phase 10) | AI Lead / 10
R-F03 | Cross-tenant leakage via 403/404 timing | 2 | 5 | 10 | Bundle-lookup 404-not-403; annual pen-test | P-PLAT / 10
R-F04 | Demo failure at TechEx (UI regression) | 2 | 4 | 8 | Pre-recorded fallback; Playwright UI-driving E2E pre-flight (CP9.52) | P-PLAT / 9.52
R-F05 | sessionStorage anti-pattern adopted in Console (mendoraci cautionary tale) | 2 | 3 | 6 | BR-14 AC-2 explicit prohibition + RT-F19; pre-emptive | Tech Lead / 9.52
R-F06 | Console-only auth coupling breaks API client-agnosticism | 2 | 4 | 8 | Per-tenant token in API layer (CP10.1) decoupled from Console | P-PLAT / 10
R-F07 | KMS envelope deferral leaves at-rest encryption gap | 3 | 4 | 12 | Phase 11 CP11.2 commitment; interim TLS-at-gateway documented | P-PLAT + Sec Lead / 11
R-F08 | M&A diligence export bundle forgery (no detached platform sig) | 2 | 4 | 8 | IMP-F04 / IMP-F05 Phase 11 | P-COUNSEL + P-PLAT / 11
R-F09 | Native Console expectation creep (sponsors pull native into v1.x) | 3 | 3 | 9 | BR-14 AC-9 explicit Phase 14+; documented in DEPLOYMENT_TOPOLOGY + Pricing Strategic tier | Product Owner / 9.52
R-F10 | PWA install adoption low (judges don't install) | 3 | 2 | 6 | Pre-install demo phone for TechEx; install QR code on JUDGE_HANDOUT | P-PLAT / 9.52
R-F11 | LangGraph (BR-07) deferral leaves multi-agent workflows unserved | 3 | 4 | 12 | Phase 12 CP12.x commitment; interim DID-based agent identity | AI Lead / 12
R-F12 | Documentation drift between canonical + LIVE (the pattern v2.0 addresses) | 4 | 3 | 12 | Rule A.10 + Rule A.11 + LIVE-update-after-every-commit cadence | Tech Lead / continuous

## 13_Change_log
Cross-doc change log
Date | Doc | Change
2026-05-18 05:15 BST | All v2.0 docs | v2.0 ELABORATED. BRD reshaped to mendoraci shape (§1..§20). BR-14 (Operator Console — Web + PWA, native deferred Phase 14+) introduced. UC-09, UC-10 added. US-F01..F32, SCR-F01..F10, RT-F01..F22, EVID-F01..F06, BG-F01..F06, R-F01..F12, OPT-F01..F08, EVAL-F01/F02, IMP-F* numbered. Rule A.11 (CP ↔ requirement closure) locked. Folder reshape with per-topic _archive/. v1 docs preserved verbatim. Supersession map records 4 v1.2-narrative-vs-HEAD drifts (BR-02, F06, F10, F11).
2026-05-17 17:50 BST | packages/crypto/tsa.py + tests | CP9.51 d7d9aaa — verify_rfc3161_timestamp_response() full PKIX cert-chain verification against FreeTSA published chain. 14 unit + live integration tests. Fixtures bundled.
2026-05-17 03:47 BST | apps/web + tests/playwright | CP9.50 b92c308 — /evidence Console page; auditex 2-crypto-op demo spec rewrite; Chromium pre-paint blank frame fix.
2026-05-15 11:22 BST | BRD + TRACEABILITY | CP9.29 — BR-12 DEFERRED → IMPLEMENTED+TESTED. Headline 9/13 → 10/13.
2026-05-15 10:55 BST | BRD + TRACEABILITY | CP9.28 — BR-13 STUB → IMPLEMENTED+TESTED. Headline 8/13 → 9/13.
2026-05-15 07:10 BST | BRD + TRACEABILITY | CP9.21a + 9.21b — BR-05 PARTIAL → IMPLEMENTED+TESTED.
2026-05-14 22:02 BST | BRD + TRACEABILITY (v1 last sweep) | CP9.17 NFR-08 retry-safe ingest at IMPLEMENTED+TESTED. CP9.16-PG-up BR-01 narrative references DB-level append-only triggers.
2026-05-12 | All v1 docs | v1 baseline frozen at 13 BRs + 8 UCs + 5 personas.